## Defect Report
Defect ID | Summary | Detected By | Defect date | Assign To | Severity | Priority | Status | Build Version | Module | Environment | Defect Type | Reproduce steps | Expected Result | Actual Result | comment
Defect_01 | Textbox input validation not working | Hetal | 2025-04-03 | NA | High | High | Open | NA | Textbox | Web | Functional | 1. Open the URL 2. Navigate to "Text Box" 3. Enter invalid characters (e.g., special symbols) | The system should prevent invalid input | The textbox accepts all inputs without validation | Data validation issue
Defect_02 | Checkbox selection not retained after refresh | Hetal | 2025-04-03 | NA | Medium | Medium | Open | NA | Checkbox | Web | Functional | 1. Open the URL 2. Navigate to "Checkbox" 3. Select a checkbox and refresh the page | Selected checkbox should remain checked | Checkbox gets unchecked after refresh | Session persistence issue
Defect_03 | UI misalignment in Forms section | Hetal | 2025-04-03 | NA | Low | Medium | Open | NA | Forms | Web | UI | 1. Open the URL 2. Navigate to "Forms" 3. Check for alignment issues | UI elements should be properly aligned | Fields are overlapping | Minor UI issue(gap between fname,lastname)
Defect_04 | Color change not applied | Hetal | 2025-04-03 | NA | Low | Medium | Open | NA | Dynamic Properties | Web | UI | 1. Open the URL 2. Click on the color changing button | Button color should change on click | Button color remains the same | Low impact, but needs fixing
Defect_05 | Text field not accepting input | Hetal | 2025-04-03 | NA | High | High | Open | NA | Dynamic Properties | Web | Functional | 1.Open the URL 2. Click on the text field 3. Try to enter text | Text field should accept user input | Text field does not accept input | Critical for user interaction
Defect_06 | Page not responsive on mobile | Hetal | 2025-04-03 | NA | High | High | Open | NA | Dynamic Properties | Web | UI | 1. Open the URL on a mobile device 2. Observe the layout | Page should be responsive and usable | Page layout breaks on mobile | Needs immediate attention
Defect_07 | Error message not displayed | Hetal | 2025-04-03 | NA | High | High | Open | NA | Practice Form | Web | Functional | 1. Open the URL 2. Leave required fields empty 3. Click Submit | Error message should display for required fields | No error message appears | Important for user feedback
Defect_08 | Frame border not visible | Hetal | 2025-04-03 | NA | Low | Low | Open | NA | Frames | Web | UI | 1.Open the URL 2. Observe the frame borders | Frame borders should be visible | Frame borders are not visible | UI issue, can be fixed later